## Okrs
Title | Team | Creator | Owner | Period | Start Date | End Date | Description | Aligned To (weight, Objective ID) | Metric Name | Unit | Target | Object Type | Goal Type | Start | Created At | Last Check-in | Progress % | Actual Progress | Status | Last Check-in Note | Score | Checkins
Prioritise high impact opps in CX ecosystem |  | Frederic Laziou | Matt Hughes | Annual 2025 | 2025-01-01 | 2025-12-31 |  | SP1: Lead with AI(weight: 0%, Id: 2295706) | Progress | % | 100 | Objective | Aspirational Goal | 0 | 2024-12-09 14:52:16 UTC |  | 0 | 0 | Not Started
Clear Success Criteria for ‘Definition of Done’ (Delivery) |  | Matt Hughes | Matt Hughes | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Prioritise high impact opps in CX ecosystem(weight: 0%, Id: 2295784) | Progress | % | 100 | Objective | Aspirational Goal | 0 | 2025-03-12 08:21:15 UTC | 2025-03-12 | 25 | 25 | Behind
100% Epics has clearly defined success criteria before development begins |  | Matt Hughes | Matt Hughes | Q1 2025 | 2025-01-01 | 2025-03-31 |  | Clear Success Criteria for ‘Definition of Done’ (Delivery)(weight: 50%, Id: 2503050) | Product Epic's | % | 100 | Key result | Aspirational Goal | 0 | 2025-03-12 08:22:31 UTC | 2025-03-12 | 30 | 30 | At Risk |  |  | Checkin Date: 2025-03-12; User: Matt Hughes; Note: ; Metric Name: Product Epic's; Status: At Risk; Current Value: 30%; Activity Date: 2025-03-12 08:31:53 UTC;
100% of team members understand and align to the definition of ‘done’ before starting work |  | Matt Hughes | Matt Hughes | Q2 2025 | 2025-04-01 | 2025-06-30 |  | Clear Success Criteria for ‘Definition of Done’ (Delivery)(weight: 50%, Id: 2503050) | Team Members | % | 100 | Key result | Aspirational Goal | 0 | 2025-03-12 08:32:55 UTC | 2025-03-12 | 20 | 20 | On Track |  |  | Checkin Date: 2025-03-12; User: Matt Hughes; Note: ; Metric Name: Team Members; Status: On Track; Current Value: 20%; Activity Date: 2025-03-12 08:34:15 UTC;
Transparency through Roadmap |  | Matt Hughes | Matt Hughes | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Prioritise high impact opps in CX ecosystem(weight: 0%, Id: 2295784) | Progress | % | 100 | Objective | Aspirational Goal | 0 | 2025-03-11 14:57:11 UTC | 2025-03-12 | 62 | 62 | Behind
100% transparency with P&T Roadmap |  | Matt Hughes | Matt Hughes | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Transparency through Roadmap(weight: 20%, Id: 2502121) | Roadmap Transparency | % | 100 | Key result | Aspirational Goal | 0 | 2025-03-11 14:58:11 UTC | 2025-03-12 | 30 | 30 | On Track |  |  | Checkin Date: 2025-03-12; User: Matt Hughes; Note: ; Metric Name: Roadmap Transparency; Status: On Track; Current Value: 30%; Activity Date: 2025-03-12 08:29:22 UTC;
Deliver Roadmap to Commercial |  | Matt Hughes | Matt Hughes | Q1 2025 | 2025-01-01 | 2025-03-31 |  | Transparency through Roadmap(weight: 20%, Id: 2502121) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-03-11 14:58:47 UTC | 2025-03-11 | 99 | 99 | On Track | Delivered Roadmap Deck to Commercial Leaders |  | Checkin Date: 2025-03-11; User: Matt Hughes; Note: Delivered Roadmap Deck to Commercial Leaders; Metric Name: Progress; Status: On Track; Current Value: 99%; Activity Date: 2025-03-11 15:01:38 UTC;
100% Adoption in product team of Productboard |  | Matt Hughes | Matt Hughes | Q1 2025 | 2025-01-01 | 2025-03-31 |  | Transparency through Roadmap(weight: 20%, Id: 2502121) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-03-11 15:14:23 UTC | 2025-03-11 | 50 | 50 | On Track |  |  | Checkin Date: 2025-03-11; User: Matt Hughes; Note: ; Metric Name: Progress; Status: On Track; Current Value: 50%; Activity Date: 2025-03-11 15:14:46 UTC;
All Puzzel enabled on Productboard |  | Matt Hughes | Matt Hughes | Q1 2025 | 2025-01-01 | 2025-03-31 |  | Transparency through Roadmap(weight: 20%, Id: 2502121) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-03-11 15:15:26 UTC | 2025-03-12 | 30 | 30 | At Risk | Enablement will not start until mid March |  | Checkin Date: 2025-03-12; User: Matt Hughes; Note: ; Metric Name: Progress; Status: At Risk; Current Value: 30%; Activity Date: 2025-03-12 08:27:23 UTC; | Checkin Date: 2025-03-11; User: Matt Hughes; Note: Enablement will not start until mid March; Metric Name: Progress; Status: Not Started; Current Value: 0%; Activity Date: 2025-03-11 15:16:30 UTC;
Product Objectives Defined in Productboard |  | Matt Hughes | Matt Hughes | Q1 2025 | 2025-01-01 | 2025-03-31 |  | Transparency through Roadmap(weight: 20%, Id: 2502121) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-03-12 05:46:37 UTC | 2025-03-12 | 100 | 100 | Closed | Objectives in Productboard | N/A | Checkin Date: 2025-03-12; User: Matt Hughes; Note: Objectives in Productboard; Metric Name: Progress; Status: Closed; Current Value: 100%; Activity Date: 2025-03-12 05:47:45 UTC;
Clear and Anchored ROI on All Investment |  | Matt Hughes | Matt Hughes | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Prioritise high impact opps in CX ecosystem(weight: 0%, Id: 2295784) | Progress | % | 100 | Objective | Aspirational Goal | 0 | 2025-03-12 05:58:12 UTC | 2025-03-12 | 13 | 13 | On Track
100% all product investment business value validated before any product work begins |  | Matt Hughes | Matt Hughes | Q2 2025 | 2025-04-01 | 2025-06-30 |  | Clear and Anchored ROI on All Investment(weight: 33.33%, Id: 2502793) | Complete |  | 100 | Key result | Aspirational Goal | 0 | 2025-03-12 08:01:52 UTC | 2025-03-12 | 20 | 20 | On Track |  |  | Checkin Date: 2025-03-12; User: Matt Hughes; Note: ; Metric Name: Complete; Status: On Track; Current Value: 20; Activity Date: 2025-03-12 08:25:04 UTC;
Business Value Template Created in PB |  | Matt Hughes | Matt Hughes | Q1 2025 | 2025-01-01 | 2025-03-31 |  | 100% all product investment business value validated before any product work begins(weight: 0%, Id: 2502969) | Progress | % | 100 | Deliverable | Committed Goal | 0 | 2025-03-12 08:04:29 UTC | 2025-03-12 | 0 | 0 | Closed | This has now been completed | 0 | Checkin Date: 2025-03-12; User: Matt Hughes; Note: This has now been completed; Metric Name: Progress; Status: Closed; Current Value: 0%; Activity Date: 2025-03-12 08:04:51 UTC;
Business Value Training for PO's |  | Matt Hughes | Matt Hughes | Q2 2025 | 2025-04-01 | 2025-06-30 |  | 100% all product investment business value validated before any product work begins(weight: 0%, Id: 2502969) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-03-12 08:09:06 UTC | 2025-03-12 | 20 | 20 | On Track |  |  | Checkin Date: 2025-03-12; User: Matt Hughes; Note: ; Metric Name: Progress; Status: On Track; Current Value: 20%; Activity Date: 2025-03-12 08:09:17 UTC;
Create Playbook for GPT usage to support Business Value Creation |  | Matt Hughes | Matt Hughes | Q2 2025 | 2025-04-01 | 2025-06-30 |  | 100% all product investment business value validated before any product work begins(weight: 0%, Id: 2502969) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-03-12 08:26:27 UTC |  | 0 | 0 | Not Started
100% of launched products have ROI tracked and measured post-launch |  | Matt Hughes | Matt Hughes | Q2 2025 | 2025-04-01 | 2025-06-30 |  | Clear and Anchored ROI on All Investment(weight: 33.33%, Id: 2502793) | Target |  | 100 | Key result | Aspirational Goal | 0 | 2025-03-12 08:06:33 UTC | 2025-03-12 | 20 | 20 | On Track |  |  | Checkin Date: 2025-03-12; User: Matt Hughes; Note: ; Metric Name: Target; Status: On Track; Current Value: 20; Activity Date: 2025-03-12 08:24:55 UTC;
All License usage in reporting |  | Matt Hughes | Matt Hughes | Q1 2025 | 2025-01-01 | 2025-03-31 |  | 100% of launched products have ROI tracked and measured post-launch(weight: 0%, Id: 2502987) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-03-12 08:13:58 UTC | 2025-03-12 | 98 | 98 | On Track |  |  | Checkin Date: 2025-03-12; User: Matt Hughes; Note: ; Metric Name: Progress; Status: On Track; Current Value: 98%; Activity Date: 2025-03-12 08:14:12 UTC;
All transactional usage in reporting |  | Matt Hughes | Matt Hughes | Q1 2025 | 2025-01-01 | 2025-03-31 |  | 100% of launched products have ROI tracked and measured post-launch(weight: 0%, Id: 2502987) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-03-12 08:14:38 UTC | 2025-03-12 | 50 | 50 | At Risk | Delays due to new end points needed in Virtual Agents and Conversational Intelligence |  | Checkin Date: 2025-03-12; User: Matt Hughes; Note: Delays due to new end points needed in Virtual Agents and Conversational Intelligence; Metric Name: Progress; Status: At Risk; Current Value: 50%; Activity Date: 2025-03-12 08:15:22 UTC; | Checkin Date: 2025-03-12; User: Matt Hughes; Note: ; Metric Name: Progress; Status: At Risk; Current Value: 50%; Activity Date: 2025-03-12 08:14:48 UTC;
All product access to new reporting |  | Matt Hughes | Matt Hughes | Q2 2025 | 2025-04-01 | 2025-06-30 |  | 100% of launched products have ROI tracked and measured post-launch(weight: 0%, Id: 2502987) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-03-12 08:16:00 UTC | 2025-03-12 | 95 | 95 | On Track |  |  | Checkin Date: 2025-03-12; User: Matt Hughes; Note: ; Metric Name: Progress; Status: On Track; Current Value: 95%; Activity Date: 2025-03-12 08:17:24 UTC; | Checkin Date: 2025-03-12; User: Matt Hughes; Note: ; Metric Name: Progress; Status: On Track; Current Value: 40%; Activity Date: 2025-03-12 08:16:48 UTC;
All product access to carr |  | Matt Hughes | Matt Hughes | Q1 2025 | 2025-01-01 | 2025-03-31 |  | 100% of launched products have ROI tracked and measured post-launch(weight: 0%, Id: 2502987) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-03-12 08:17:48 UTC | 2025-03-12 | 50 | 50 | At Risk | Not available in Snowflake yet |  | Checkin Date: 2025-03-12; User: Matt Hughes; Note: Not available in Snowflake yet; Metric Name: Progress; Status: At Risk; Current Value: 50%; Activity Date: 2025-03-12 08:18:16 UTC; | Checkin Date: 2025-03-12; User: Matt Hughes; Note: ; Metric Name: Progress; Status: At Risk; Current Value: 50%; Activity Date: 2025-03-12 08:18:03 UTC;
All main products to have product analytics |  | Matt Hughes | Matt Hughes | Q2 2025 | 2025-04-01 | 2025-06-30 |  | 100% of launched products have ROI tracked and measured post-launch(weight: 0%, Id: 2502987) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-03-12 08:19:17 UTC | 2025-03-12 | 10 | 10 | On Track |  |  | Checkin Date: 2025-03-12; User: Matt Hughes; Note: ; Metric Name: Progress; Status: On Track; Current Value: 10%; Activity Date: 2025-03-12 08:19:32 UTC;
100% of Backlog Items Prioritised using RICE |  | Matt Hughes | Matt Hughes | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Clear and Anchored ROI on All Investment(weight: 33.33%, Id: 2502793) | RICE |  | 100 | Key result | Aspirational Goal | 0 | 2025-03-12 08:24:08 UTC |  | 0 | 0 | Not Started
Drive Business Growth Through Strategic Product Investments |  | Matt Hughes | Matt Hughes | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Prioritise high impact opps in CX ecosystem(weight: 0%, Id: 2295784) | Progress | % | 100 | Objective | Aspirational Goal | 0 | 2025-03-12 08:36:13 UTC |  | 0 | 0 | Not Started
All product work is explicitly linked to strategic product goals |  | Matt Hughes | Matt Hughes | Q2 2025 | 2025-04-01 | 2025-06-30 |  | Drive Business Growth Through Strategic Product Investments(weight: 33.33%, Id: 2503108) | Product worked linked |  | 100 | Key result | Aspirational Goal | 0 | 2025-03-12 08:36:52 UTC |  | 0 | 0 | Not Started
Implement Goal Mapping in Productboard |  | Matt Hughes | Matt Hughes | Q1 2025 | 2025-01-01 | 2025-03-31 |  | All product work is explicitly linked to strategic product goals(weight: 0%, Id: 2503112) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-03-12 08:42:11 UTC | 2025-03-12 | 80 | 80 | On Track |  |  | Checkin Date: 2025-03-12; User: Matt Hughes; Note: ; Metric Name: Progress; Status: On Track; Current Value: 80%; Activity Date: 2025-03-12 08:42:24 UTC;
Each team member can articulate how their work contributes to business growth |  | Matt Hughes | Matt Hughes | Q2 2025 | 2025-04-01 | 2025-06-30 |  | Drive Business Growth Through Strategic Product Investments(weight: 33.33%, Id: 2503108) | Team members | % | 100 | Key result | Aspirational Goal | 0 | 2025-03-12 08:37:30 UTC |  | 0 | 0 | Not Started
% of Product Initiatives with Business Impact Data Attached |  | Matt Hughes | Matt Hughes | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Drive Business Growth Through Strategic Product Investments(weight: 33.33%, Id: 2503108) | Business Impact | % | 50 | Key result | Aspirational Goal | 0 | 2025-03-12 08:40:16 UTC |  | 0 | 0 | Not Started
Improve product GTM |  | Frederic Laziou | Gabi Warren, Matt Hughes | Annual 2025 | 2025-01-01 | 2025-12-31 |  | SP1: Lead with AI(weight: 0%, Id: 2295706) | Progress | % | 100 | Objective | Aspirational Goal | 0 | 2024-12-09 14:52:32 UTC | 2025-07-23 | 25 | 25 | At Risk
Packaging & pricing |  | Frederic Laziou | Frederic Laziou | Q2 2025 | 2025-04-01 | 2025-06-30 |  | Improve product GTM(weight: 0%, Id: 2295785) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2024-12-17 12:14:13 UTC | 2025-08-19 | 0 | 0 | Postponed | Postponed due to limited bandwidth. Will be addressed early 2026. |  | Checkin Date: 2025-08-19; User: Frederic Laziou; Note: Postponed due to limited bandwidth. Will be addressed early 2026.; Metric Name: Progress; Status: Postponed; Current Value: 0%; Activity Date: 2025-08-19 10:20:04 UTC; | Checkin Date: 2025-05-19; User: Frederic Laziou; Note: Postponed; Metric Name: Progress; Status: Not Started; Current Value: 0%; Activity Date: 2025-05-19 09:31:38 UTC;
Launch process | Marketing | Gabi Warren | Gabi Warren, Matt Hughes, Raïsa Van Olden | Annual 2025 | 2025-01-01 | 2025-12-31 | Deliver a launch framework, and launch Virtual Agents, as well as analytics | Improve product GTM(weight: 0%, Id: 2295785) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-02-10 10:46:03 UTC | 2025-04-14 | 80 | 80 | On Track | CI launch review happened on 11 March. CI will be our next launch in May, at Elevate Virtual. |  | Checkin Date: 2025-04-14; User: Gabi Warren; Note: ; Metric Name: Progress; Status: On Track; Current Value: 80%; Activity Date: 2025-04-14 08:30:36 UTC; | Checkin Date: 2025-03-12; User: Gabi Warren; Note: CI launch review happened on 11 March. CI will be our next launch in May, at Elevate Virtual.; Metric Name: Progress; Status: On Track; Current Value: 40%; Activity Date: 2025-03-12 09:42:17 UTC; Comment #1 [2025-03-13 08:28:17 UTC, Morgan Sandberg]:I believe you meant to write VA instead of CI in the first sentence.; Comment #2 [2025-03-13 08:42:06 UTC, Gabi Warren]:No. Virtual Agents are launched. We'll be launching Conversational Intelligence.; Comment #3 [2025-03-13 09:30:24 UTC, Morgan Sandberg]:Sorry I missed the word "review", so I thought you were referring to the VA launch.; | Checkin Date: 2025-02-10; User: Gabi Warren; Note: ; Metric Name: Progress; Status: On Track; Current Value: 25%; Activity Date: 2025-02-10 10:46:14 UTC;
Product naming | Marketing | Gabi Warren | Gabi Warren, Matt Hughes | Annual 2025 | 2025-01-01 | 2025-03-31 |  | Improve product GTM(weight: 0%, Id: 2295785) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-02-11 10:12:07 UTC | 2025-04-14 | 100 | 100 | On Track | Naming agreed, logos nearly ready and being shown during the product presentation at Elevate. |  | Checkin Date: 2025-04-14; User: Gabi Warren; Note: ; Metric Name: Progress; Status: On Track; Current Value: 100%; Activity Date: 2025-04-14 08:30:48 UTC; | Checkin Date: 2025-03-12; User: Gabi Warren; Note: Naming agreed, logos nearly ready and being shown during the product presentation at Elevate.; Metric Name: Progress; Status: On Track; Current Value: 80%; Activity Date: 2025-03-12 09:42:56 UTC; | Checkin Date: 2025-03-03; User: Gabi Warren; Note: ; Metric Name: Progress; Status: Behind; Current Value: 65%; Activity Date: 2025-03-03 09:32:28 UTC; | Checkin Date: 2025-02-19; User: Gabi Warren; Note: ; Metric Name: Progress; Status: Behind; Current Value: 50%; Activity Date: 2025-02-19 09:36:37 UTC; | Checkin Date: 2025-02-11; User: Gabi Warren; Note: Marc and Kristian working on design. Tobias working on naming. To be presented to GLT on 12 Feb.; Metric Name: Progress; Status: Behind; Current Value: 30%; Activity Date: 2025-02-11 10:14:08 UTC;
Deliver a competitive intelligence programme | Marketing | Gabi Warren | Gabi Warren, Raïsa Van Olden | Annual 2025 | 2025-04-01 | 2025-06-30 |  | Improve product GTM(weight: 0%, Id: 2295785) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-03-12 12:25:43 UTC | 2025-04-14 | 50 | 50 | On Track |  |  | Checkin Date: 2025-04-14; User: Gabi Warren; Note: ; Metric Name: Progress; Status: On Track; Current Value: 50%; Activity Date: 2025-04-14 08:30:17 UTC; | Checkin Date: 2025-03-12; User: Gabi Warren; Note: ; Metric Name: Progress; Status: On Track; Current Value: 19%; Activity Date: 2025-03-12 12:26:16 UTC;
Value proposition/ USPs | Marketing | Gabi Warren | Gabi Warren, Matt Hughes, Roland Green | Annual 2025 | 2025-04-01 | 2025-06-30 |  | Improve product GTM(weight: 0%, Id: 2295785) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-03-12 12:28:00 UTC | 2025-04-14 | 0 | 0 | Not Started |  |  | Checkin Date: 2025-04-14; User: Gabi Warren; Note: ; Metric Name: Progress; Status: Not Started; Current Value: 0%; Activity Date: 2025-04-14 08:30:26 UTC;
Deliver one launch in H1 |  | Gabi Warren | Gabi Warren, Matt Hughes | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Improve product GTM(weight: 100%, Id: 2295785) | Progress | % | 100 | Key result | Aspirational Goal | 0 | 2025-03-12 13:04:35 UTC | 2025-03-12 | 25 | 25 | On Track | CI in progress |  | Checkin Date: 2025-03-12; User: Gabi Warren; Note: CI in progress; Metric Name: Progress; Status: On Track; Current Value: 25%; Activity Date: 2025-03-12 13:05:03 UTC;
Drive customer adoption through successful product launches | Marketing | Raïsa Van Olden | Raïsa Van Olden | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Improve product GTM(weight: 0%, Id: 2295785) | Progress | % | 100 | Objective | Aspirational Goal | 0 | 2025-07-23 15:19:10 UTC | 2025-07-23 | 75 | 75 | On Track
Co-Pilot Launch for Customer, prospects and partners | Marketing | Raïsa Van Olden | Raïsa Van Olden | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Drive customer adoption through successful product launches(weight: 100%, Id: 2844416) | Progress | % | 100 | Key result | Aspirational Goal | 0 | 2025-07-23 15:20:35 UTC | 2025-07-23 | 75 | 75 | On Track |  |  | Checkin Date: 2025-07-23; User: Raïsa Van Olden; Note: ; Metric Name: Progress; Status: On Track; Current Value: 75%; Activity Date: 2025-07-23 15:25:20 UTC;
Launch Kit for Co Pilot (commercial enablement) | Marketing | Raïsa Van Olden | Raïsa Van Olden | Q3 2025 | 2025-07-01 | 2025-09-30 |  | Co-Pilot Launch for Customer, prospects and partners(weight: 0%, Id: 2844418) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-07-23 15:24:45 UTC | 2025-07-23 | 60 | 60 | On Track |  |  | Checkin Date: 2025-07-23; User: Raïsa Van Olden; Note: ; Metric Name: Progress; Status: On Track; Current Value: 60%; Activity Date: 2025-07-23 15:25:12 UTC;
Integrate Discovery & Innovation in SDLC |  | Frederic Laziou | Matt Hughes, Signe Roesgaard-Gran | Annual 2025 | 2025-01-01 | 2025-12-31 |  | SP2: Customer excellence(weight: 0%, Id: 2295711) | Progress | % | 100 | Objective | Aspirational Goal | 0 | 2024-12-09 14:54:13 UTC | 2025-03-12 | 50 | 50 | On Track
100% Product Aligned Product Org |  | Matt Hughes | Matt Hughes | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Integrate Discovery & Innovation in SDLC(weight: 100%, Id: 2295798) | Aligned | % | 100 | Key result | Aspirational Goal | 0 | 2025-03-12 12:36:24 UTC | 2025-03-12 | 50 | 50 | Behind | Lots of moving parts with product organisation |  | Checkin Date: 2025-03-12; User: Matt Hughes; Note: ; Metric Name: Aligned; Status: Behind; Current Value: 50%; Activity Date: 2025-03-12 13:51:28 UTC; | Checkin Date: 2025-03-12; User: Matt Hughes; Note: Lots of moving parts with product organisation; Metric Name: Aligned; Status: On Track; Current Value: 50%; Activity Date: 2025-03-12 12:37:41 UTC;
Migrate customers from Vergic platform |  | Jan Rygh | Jan Rygh, Matt Hughes | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Simplify platform(weight: 25%, Id: 2433565) | Customers migrated | % | 100 | Key result | Aspirational Goal | 1 | 2025-02-05 09:23:10 UTC | 2025-10-15 | 76.7677 | 77 | Behind | 184 customers closed/migrated. 85 accounts still active |  | Checkin Date: 2025-10-15; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: Behind; Current Value: 77%; Activity Date: 2025-10-15 09:48:14 UTC; | Checkin Date: 2025-07-03; User: Jan Rygh; Note: 184 customers closed/migrated. 85 accounts still active; Metric Name: Customers migrated; Status: On Track; Current Value: 71%; Activity Date: 2025-07-03 07:09:18 UTC; | Checkin Date: 2025-06-19; User: Jan Rygh; Note: 182 customers migrated; Metric Name: Customers migrated; Status: On Track; Current Value: 71%; Activity Date: 2025-06-19 07:35:41 UTC; | Checkin Date: 2025-06-02; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: On Track; Current Value: 71%; Activity Date: 2025-06-02 14:18:40 UTC; | Checkin Date: 2025-06-02; User: Jan Rygh; Note: 179 accounts removed; Metric Name: Customers migrated; Status: On Track; Current Value: 68%; Activity Date: 2025-06-02 14:17:03 UTC; | Checkin Date: 2025-05-15; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: On Track; Current Value: 68%; Activity Date: 2025-05-15 08:13:09 UTC; | Checkin Date: 2025-03-27; User: Jan Rygh; Note: We have removed 169 accounts from the Vergic platform where we did not see any traffic anymore. So 100 accounts remains; Metric Name: Customers migrated; Status: On Track; Current Value: 63%; Activity Date: 2025-03-27 09:11:04 UTC; | Checkin Date: 2025-03-27; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: On Track; Current Value: 63%; Activity Date: 2025-03-27 09:09:35 UTC; | Checkin Date: 2025-03-10; User: Jan Rygh; Note: We have 270 accounts on the vergic platform that need to be turned off. In addition to migrating, we will need to remove unused accounts and also customers that will not migrate; Metric Name: Customers migrated; Status: Behind; Current Value: 1%; Activity Date: 2025-03-10 12:08:45 UTC; | Checkin Date: 2025-03-10; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: Behind; Current Value: 1%; Activity Date: 2025-03-10 12:07:15 UTC; | Checkin Date: 2025-03-10; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: Behind; Current Value: 2%; Activity Date: 2025-03-10 12:07:00 UTC; | Checkin Date: 2025-02-25; User: Jan Rygh; Note: Even though 5 customers would not migrate, they are still on the platform, so wrong to add them to migrated status before they are off the platform; Metric Name: Customers migrated; Status: Behind; Current Value: 1%; Activity Date: 2025-02-25 15:05:50 UTC; | Checkin Date: 2025-02-25; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: Behind; Current Value: 1%; Activity Date: 2025-02-25 15:04:59 UTC; | Checkin Date: 2025-02-15; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: Behind; Current Value: 1%; Activity Date: 2025-02-15 13:54:14 UTC; | Checkin Date: 2025-02-15; User: Jan Rygh; Note: 5 customers will not migrate; Metric Name: Customers migrated; Status: Behind; Current Value: 1%; Activity Date: 2025-02-15 13:54:08 UTC; | Checkin Date: 2025-02-15; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: Behind; Current Value: 1%; Activity Date: 2025-02-15 13:50:03 UTC; | Checkin Date: 2025-02-10; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: On Track; Current Value: 1%; Activity Date: 2025-02-10 14:24:14 UTC;
Migrate PuzzelID customers |  | Jan Rygh | Jan Rygh, Matt Hughes | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Simplify platform(weight: 25%, Id: 2433565) | Customers migrated | % | 80 | Key result | Aspirational Goal | 1 | 2025-02-05 09:29:18 UTC | 2025-10-15 | 8.8608 | 8 | At Risk | 71 customers with more than 80% of agents logged into Puzzel ID |  | Checkin Date: 2025-10-15; User: Jan Rygh; Note: 71 customers with more than 80% of agents logged into Puzzel ID; Metric Name: Customers migrated; Status: At Risk; Current Value: 8%; Activity Date: 2025-10-15 09:22:04 UTC; | Checkin Date: 2025-10-15; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: At Risk; Current Value: 8%; Activity Date: 2025-10-15 09:21:12 UTC; | Checkin Date: 2025-07-03; User: Jan Rygh; Note: 52 customers with more than 80% of agents logged into Puzzel ID; Metric Name: Customers migrated; Status: At Risk; Current Value: 6%; Activity Date: 2025-07-03 07:12:31 UTC; | Checkin Date: 2025-06-19; User: Jan Rygh; Note: 49 customers with more than 80% of agents logging in through Puzzel ID; Metric Name: Customers migrated; Status: At Risk; Current Value: 6%; Activity Date: 2025-06-19 07:37:14 UTC; | Checkin Date: 2025-06-02; User: Jan Rygh; Note: 56 customers migrated. Total number of customers needed to be migrated is reduced from 1766 to 918, therefor increase from 3% to 6%; Metric Name: Customers migrated; Status: At Risk; Current Value: 6%; Activity Date: 2025-06-02 14:15:12 UTC; | Checkin Date: 2025-06-02; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: At Risk; Current Value: 6%; Activity Date: 2025-06-02 14:11:07 UTC; | Checkin Date: 2025-05-15; User: Jan Rygh; Note: 53 customers migrated; Metric Name: Customers migrated; Status: At Risk; Current Value: 3%; Activity Date: 2025-05-15 08:16:42 UTC; | Checkin Date: 2025-05-15; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: At Risk; Current Value: 3%; Activity Date: 2025-05-15 08:16:27 UTC; | Checkin Date: 2025-05-15; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: Behind; Current Value: 6%; Activity Date: 2025-05-15 08:15:42 UTC; | Checkin Date: 2025-03-27; User: Jan Rygh; Note: 41 customers migrated; Metric Name: Customers migrated; Status: Behind; Current Value: 2%; Activity Date: 2025-03-27 09:11:47 UTC; | Checkin Date: 2025-03-10; User: Jan Rygh; Note: 36 customers migrated; Metric Name: Customers migrated; Status: Behind; Current Value: 2%; Activity Date: 2025-03-10 11:51:13 UTC; | Checkin Date: 2025-03-10; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: Behind; Current Value: 2%; Activity Date: 2025-03-10 11:50:36 UTC; | Checkin Date: 2025-02-25; User: Jan Rygh; Note: 33 customers migrated; Metric Name: Customers migrated; Status: Behind; Current Value: 2%; Activity Date: 2025-02-25 15:04:08 UTC; | Checkin Date: 2025-02-25; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: Behind; Current Value: 2%; Activity Date: 2025-02-25 15:01:54 UTC; | Checkin Date: 2025-02-15; User: Jan Rygh; Note: 24 customers out of 1766 migrated so far; Metric Name: Customers migrated; Status: On Track; Current Value: 1%; Activity Date: 2025-02-15 13:54:47 UTC; | Checkin Date: 2025-02-10; User: Jan Rygh; Note: ; Metric Name: Customers migrated; Status: On Track; Current Value: 1%; Activity Date: 2025-02-10 14:26:02 UTC;
Help Centre moved into the new brand | Marketing | Gabi Warren | Gabi Warren, Matt Hughes | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Strategic Enabler 3: Brand(weight: 0%, Id: 2445320) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-02-10 11:01:18 UTC | 2025-04-14 | 20 | 20 | On Track |  |  | Checkin Date: 2025-04-14; User: Gabi Warren; Note: ; Metric Name: Progress; Status: On Track; Current Value: 20%; Activity Date: 2025-04-14 08:31:07 UTC; | Checkin Date: 2025-03-12; User: Gabi Warren; Note: ; Metric Name: Progress; Status: On Track; Current Value: 20%; Activity Date: 2025-03-12 08:31:41 UTC; Comment #1 [2025-03-12 08:32:12 UTC, Gabi Warren]:Articles being transferred into Knowledgebase, being tagged for redesign or update.;
Develop and create dashboard suite, with cross functional data streams |  | Stephen Grist | Emma Aspfors, Matt Hughes, Nikki Aston | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Business intelligence(weight: 0%, Id: 2725085) | Progress | % | 100 | Objective | Aspirational Goal | 0 | 2025-04-09 06:08:31 UTC | 2025-09-08 | 20 | 20 | At Risk |  |  | Checkin Date: 2025-09-08; User: Emma Aspfors; Note: ; Metric Name: Progress; Status: At Risk; Current Value: 20%; Activity Date: 2025-09-08 11:16:32 UTC;
Structure for architecture & documentation of data tables |  | Nikki Aston | Nikki Aston, Stephen Grist | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Develop and create dashboard suite, with cross functional data streams(weight: 0%, Id: 2725897) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-04-23 12:24:57 UTC | 2025-05-12 | 10 | 10 | At Risk |  |  | Checkin Date: 2025-05-12; User: Stephen Grist; Note: ; Metric Name: Progress; Status: At Risk; Current Value: 10%; Activity Date: 2025-05-12 09:29:23 UTC;
Establish data governance process |  | Nikki Aston | Nikki Aston, Stephen Grist | Annual 2025 | 2025-01-01 | 2025-12-31 |  | Develop and create dashboard suite, with cross functional data streams(weight: 0%, Id: 2725897) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-05-23 07:37:20 UTC | 2025-06-09 | 20 | 20 | Behind |  |  | Checkin Date: 2025-06-09; User: Stephen Grist; Note: ; Metric Name: Progress; Status: Behind; Current Value: 20%; Activity Date: 2025-06-09 09:37:34 UTC;
Create structure to develop prioritisation of reporting |  | Nikki Aston | Anna Pavlova, Nikki Aston | Q2 2025 | 2025-04-01 | 2025-06-30 |  | Develop and create dashboard suite, with cross functional data streams(weight: 0%, Id: 2725897) | Progress | % | 100 | Deliverable | Aspirational Goal | 0 | 2025-07-01 12:25:09 UTC | 2025-07-01 | 100 | 100 | On Track |  |  | Checkin Date: 2025-07-01; User: Nikki Aston; Note: ; Metric Name: Progress; Status: On Track; Current Value: 100%; Activity Date: 2025-07-01 12:25:25 UTC;